## Permit Log
Permit ID | Project Name | Project Address | Permit Type | Application Date | Applicant Name | Applicant Contact | Reviewer Assigned | Review Status | Additional Info Requested | Info Received Date | Approval Date | Permit Expiration | Inspection Dates | Inspection Results | Final Approval Date | Comments
P-2025-001 | Main Street Renovation | 123 Main St, Anytown | Building Alteration | 01/15/2025 | John Smith | john.smith@email.com | Mary Johnson | Approved | No |  | 02/05/2025 | 08/05/2025 | 02/28/2025, 03/15/2025 | Pass, Pass | 03/20/2025 | Project completed ahead of schedule
P-2025-002 | Oak Plaza Development | 456 Oak Ave, Anytown | New Construction | 02/03/2025 | Sarah Williams | swilliams@construction.com | Tom Lee | In Review | Yes | 03/01/2025 | [5 empty] | Structural calculations requested
P-2025-003 | Elm Street Roofing | 789 Elm St, Anytown | Roof Repair | 02/10/2025 | Robert Johnson | rjohnson@roofers.com | Linda Chen | Approved | No |  | 02/25/2025 | 08/25/2025 | 03/10/2025 | Pass | 03/12/2025
P-2025-004 | Maple Court Addition | 321 Maple Ct, Anytown | Building Addition | 02/18/2025 | David Miller | dmiller@homes.net | Mary Johnson | Additional Info Required | Yes | [6 empty] | Zoning variance needed
P-2025-005 | Pine Street Demolition | 567 Pine St, Anytown | Demolition | 03/01/2025 | Michael Brown | mbrown@demo.com | Tom Lee | Approved | No |  | 03/15/2025 | 09/15/2025 |  |  |  | Environmental clearance verified

## Statistics
Metric | Count | Percentage
Total Permits | 5 | 100%
Approved Permits | 3 | 60%
Pending Review | 1 | 20%
Additional Info Required | 1 | 20%
Expired Permits | 0 | 0%